## Slide 1
| The API and Data Foundation for Agentic Commerce
PROJECT KICK-OFF · MARCH 30, 2026
Conscia: Beyond Traditional PIM
A governed semantic foundation and real-time orchestration engine for complex, configurable commerce
POWERED BY: DX GRAPH + DX ENGINE
Conscia × Lovesac Joint Kick-off

## Slide 2
Today's Agenda
01
Why We're Here
Business context, the SKU complexity challenge, and what success looks like
02
The Solution
DX Graph as product master + DX Engine as the real-time orchestration layer
03
Project Scope
Deliverables, phasing, and what's out of scope for Phase 1
04
Team & Governance
Roles, responsibilities, working cadence, and escalation paths
05
Open Questions
Items we need Lovesac to confirm to unlock key workstreams
06
Next Steps
Actions, owners, and target dates coming out of today
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 3
The Semantic Foundation for Complex, Configurable Commerce
Conscia unifies product data, relationships, and rules into one governed foundation — served in real time to every channel, system, and agent.
Traditional PIM
manages product attributes "at rest" — batch updates, custom integrations, rules hardcoded across apps.
Result: rule debt, variant explosion, cart → BOM mismatch, slower launches.
→
Conscia
delivers real-time, deterministic outcomes — eligibility, compatibility, entitlements, and BOM results — through APIs every channel can rely on.
01
SEMANTIC FOUNDATION
Product Graph
A graph-based repository that models entities, attributes, and relationships as connected data — not flat SKU records. Lovesac's configurable Sactional system — components, covers, inserts, compatibility — lives here as first-class connected knowledge.
SKU + Configuration + Taxonomy Collections
COMPATIBLE_WITH, BUNDLES, CONTAINS relationships
Up to 3 taxonomy views for any channel
02
NATIVE RULES ENGINE
DX Engine
A deterministic rules engine that evaluates eligibility, compatibility, constraints, and entitlements at runtime — not in batch. No more hardcoded logic scattered across apps.
Configuration Validation flow
Wizard Step Options flow (POS + web)
Channel-specific Experience Rules (Quickship, Outdoor)
03
REAL-TIME EXPERIENCE APIs
Every Channel. One Truth.
Experience APIs serve consistent product decisions to every channel and agent — from POS terminals to Lovesac.com to AI shopping agents like Google Shopping and ChatGPT.
Config ID Creation + BOM Explosion
Agentic Commerce via MCP (Google, ChatGPT)
POS, web, marketplace — same governed answers
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 4
Why We're Here
Lovesac's Sactional is a highly configurable modular furniture system — and that configurability creates massive data complexity at scale.
01
13+
Attribute
Dimensions
driving
SKU explosion
THE CORE CHALLENGE
DATA MODEL
No Compatibility Model
Rules governing which covers, inserts, and components work together are implicit — not encoded as data relationships. This blocks real-time validation.
INFRASTRUCTURE
Fragmented Source Systems
Product data is distributed across up to 3 backends with no unified transformation pipeline, no canonical taxonomy, and no single source of truth.
CHANNELS
No Real-Time Orchestration
Config validation, BOM explosion, and wizard step logic have no API-first foundation — blocking POS efficiency and AI shopping agent use cases.
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 5
The Solution
Two complementary platform capabilities that together make Conscia the governed product master for Lovesac.
02
DX GRAPH
Governed Product Data Layer
"What is true?"
Single unified SKU Collection — all brands, lines, and roles in one graph
Compatibility relationships: Cover → Insert (dynamic), Finished Good composition, Taxonomy mappings
Up to 3 parallel Taxonomy Collections (internal ops, Lovesac.com, marketplace channels)
Data loaded from up to 3 source backends via Jobs (batch, API, or file ingestion)
System of record — not a cache. All downstream channels query DX Graph.
DX ENGINE
Real-Time Orchestration Layer
"What should happen?"
Configuration Validation: verify any Sactional build in real time against graph relationships
Visual Configurator: power the step-by-step wizard with valid next options
Config ID Creation: write validated builds to DX Graph as durable Config IDs
BOM Explosion: resolve a Config ID to a channel-shaped Bill of Materials
Agentic Commerce ready: flows exposable as MCP tools for Google Shopping, ChatGPT
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 6
End-to-End Architecture
SOURCE BACKENDS
Batch feeds · API pulls · File ingestion via Data Buckets — with transformation & normalisation via Jobs
▼
DX GRAPH — Governed Semantic Layer
SKU Collection · Configuration Collection · Taxonomy Collections · COMPATIBLE_WITH · BUNDLES · CONTAINS · MAPS_TO
▼
DX ENGINE — Orchestration Layer (Experience API)
Config Validation · Wizard Step Options · Config ID Creation · BOM Explosion · Channel Feeds
▼
CHANNELS
POS Systems · Lovesac.com · On-site Shopping Agent · Google Shopping · ChatGPT / 3rd-Party AI Agents
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 7
Project Scope
03
DX GRAPH
DX Graph Application provisioning
SKU, Configuration & Taxonomy Collections (up to 3 taxonomies)
COMPATIBLE_WITH, BUNDLES, CONTAINS, MAPS_TO relationships
Data ingest from up to 3 source backends via Jobs
Update up to 2 existing marketplace feeds
DX ENGINE (POC)
Configuration Validation orchestration flow
Visual Configurator wizard step options flow
Config ID Creation flow
Config ID → BOM Explosion flow
Experience Rules for series & channel constraints
OUT OF SCOPE — PHASE 1
Lovesac.com frontend integration
Real-time inventory availability
Full agentic channel (MCP) production deployment
Pricing engine integration
OMS / fulfilment system integration
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 8
Implementation Timeline
PHASE 1
Weeks 1–3
Foundation & Data
Provision DX Graph environment
Model SKU & Configuration Collections
Configure data ingest Jobs (3 backends)
Build COMPATIBLE_WITH Dynamic Relationship
PHASE 2
Weeks 4–6
Taxonomy & Feeds
Model 3 Taxonomy Collections
Map all SKUs to taxonomies
Update 2 marketplace feeds
Validate data completeness
PHASE 3
Weeks 7–10
DX Engine POC
Build Config Validation flow
Build Wizard Step Options flow
Build Config ID Creation flow
Build BOM Explosion flow
PHASE 4
Weeks 11–12
Testing & Handoff
End-to-end integration testing
Channel-specific QA (POS, web)
Documentation & runbooks
Knowledge transfer to Lovesac
Note: Timeline is indicative. Final schedule to be agreed with Lovesac based on data readiness and open question resolution.

## Slide 9
Team & Governance
04
TEAM STRUCTURE
Role
Conscia
Lovesac
Executive Sponsor
Sana Remekie
Amelia Jacobs
Project Lead
Conscia PM
Lovesac PM
Solution Architect
David U
—
Conscia Solution Engineer
Laurel Aquino
Lovesac Data Owner
Conscia Platform Engineer
Harshil Maniar
Lovesac Tech Lead
QA / Testing
Conscia QA
Lovesac QA
WORKING CADENCE
Weekly
Project Standup
30 min · Both teams · Status, blockers, decisions
Bi-weekly
Steering Check-in
60 min · Leads only · Scope, risks, milestones
As-needed
Technical Review
Data model, API design, integration reviews
End of Phase
Phase Gate Review
Demo, sign-off, and next phase kick-off
Ongoing
Slack / async comms
Shared channel for day-to-day coordination
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 10
Open Questions
These items require Lovesac input to unlock key workstreams — we'll aim to resolve them during kick-off.
05
Q1
Which 3 source backends will be ingested?
Format (API vs. file) significantly affects implementation approach and timeline.
Q2
What are the 3 taxonomy versions required?
Internal taxonomy known. Marketplace schema (Google, ChatGPT) needs confirmation.
Q3
Which 2 marketplace feeds will be updated?
Feed format, update frequency, and API vs. file determines the integration pattern.
Q4
What is the Config ID format requirement?
Does Lovesac need a specific format, or integration with an existing OMS?
Q5
Is Quickship a product type flag or live inventory?
Currently modelled as classification. Live inventory requires a different integration.
Q6
What are the Sactional component adjacency rules?
Which component types can sit next to each other? An adjacency matrix or free-connect confirmation.
Lovesac × Conscia · Project Kick-off · March 30, 2026

## Slide 11
Next Steps
Actions coming out of today's session — owners and target dates for both teams.
06
By March 31
Both
Confirm and distribute kick-off notes, decisions, and open question owners
By April 3
Lovesac
Provide list of 3 source backends (format, access method) and 2 marketplace feeds to be updated
By April 3
Lovesac
Confirm 3 taxonomy versions required; share existing internal taxonomy documentation
By April 3
Lovesac
Provide component adjacency rules OR confirm within-series free-connect (resolves Open Question 6)
By April 7
Conscia
Provision DX Graph environment and share access credentials with Lovesac team
April 7
Both
First weekly project standup — review data readiness and confirm Phase 1 sprint plan
Let's build something great together. Welcome to the project.