## Sheet1
Tasks | Owner | Status
Onboard Data
Define target data model for the DX Graph
Define a Conscia job with data transformations to convert the data from source schema to target schema
Onboard data from custom and legacy applications through batch files in xml, json or delimited file formats.
Load data from webservice API endpoints where applicable
Schedule data import jobs when ready to operationalize
Configure Editor Experience
Define the Left Nav on all pages including Sources, Master, Taxonomies
Define the data model using the Schema Builder and configure editor interface for business users
Configure read-only fields where system of record is outside of the DX Graph and we don't want them to be overridden
Create override fields and shadow fields
Enforce validation criteria when editing data attributes
Show/Hide fields in the record grid
Define Field groupings in record editor
Define HTML view for Master collections such as the product catalog
Build Relationships Between Collections
Create 1:1 Lookup relationships between collections eg. product related content from CMS
Create 1:Many relationships between collections eg. bundles
Understand and Convert compatibility rules and constraints from source systems into DX Graph schema
Create Dynamic relationships between collections eg. compatibility rules and constraints
Data Validation & Enrichment
Configure Inspector cards for each data collection to identify gaps and inconsistencies
Create Taxonomies and configure rules for assignment
Sharing Data with Downstream Systems
Document API endpoints to retrieve data and relationships in real-time from consumer touchpoints
Define data model and data transformations required for downstream systems and marketplaces
Schedule a job to push data to downstream systems
Define Webhooks and triggers to update data in target systems such as the search index
Channel Readiness & Views
Configurable Inspector cards for each data collection
Data Completeness Checks
Channel and Geography Specific Catalog Views
Define channel specific product attributes
Multi-language Support
Workflows and Permissions
Implement Role-level access to data collections
Create custom workflows such as 'Approve' or mark records as 'Ready to Publish' using the Event/Trigger Feature